404200 / DIGITAL GROWTH PROPOSAL

AMSA, easier to find.

A six-month search, content, social and website programme for AMSA Architects

Prepared for AMSA Architects  /  20 October 2026

THE PROPOSAL IN ONE SENTENCE Turn AMSA's existing architectural record into a steady system of discoverable project stories, credible profiles, useful social content and a maintainable website.

01 / THE OPPORTUNITY

# AMSA already has the proof. The next step is making that proof easier to discover.

AMSA's website presents a strong visual portfolio and identifies the practice as an award-winning architecture studio in Cyprus. The public About page records a practice founded in 2005 with residential, commercial and public experience, competition recognition and publication history.

The opportunity is mainly explanatory. Several portfolio and competition entries are shown with internal project codes and limited searchable narrative. An architect immediately understands the value of a drawing set with labels, legends and specifications; the same principle applies online. Images show the work, while descriptive project pages explain location, brief, constraints, response, material choices, team, awards and outcomes.

A PRACTICAL EXAMPLE A page called “0066-03” asks the visitor to interpret the image alone. A page titled “Courtyard Residence in [Location]” can explain the brief, site, climate response, privacy strategy and material palette, while keeping confidential facts private.

## What this programme is designed to achieve

- Help the right prospective clients find AMSA for relevant services, project types and locations.

- Give decision-makers enough context to understand AMSA's thinking, not only view photographs.

- Create a repeatable publishing system from material AMSA already produces: photographs, drawings, award submissions, project notes and site updates.

- Protect the visual character of the existing website while making future updates easier to manage.

- Measure progress through visibility, qualified visits, engagement and enquiries rather than isolated ranking screenshots.

Evidence: AMSA homepage  ·  About AMSA  ·  Competitions & Awards

02 / MONTHLY SERVICE

# What AMSA receives every month

The fee reserves a focused amount of strategy, writing, design, publishing and technical implementation each month. Work moves through one priority queue so the activity supports the most valuable commercial objective rather than producing disconnected tasks.

| Workstream | Included activity | Visible evidence |
| --- | --- | --- |
| Search direction | One rolling priority review: demand, competitors, services, locations and the next 90 days. | Updated priority list |
| Technical SEO | One SPIDEY crawl/index review plus implementation of the most important accessible fixes. | Issue log + completed fixes |
| On-page SEO | Up to two priority pages improved or prepared: titles, headings, copy, links, images and search information. | Before/after record |
| Content | One substantial project story or blog article, or two shorter website improvements, using approved AMSA facts and images. | Published website URLs |
| Social | Four core stories adapted into up to eight publications across up to three agreed channels; up to four branded assets. One carousel may replace one static item. | Scheduled/published links |
| Local SEO | Google Business Profile care, one suitable update, information consistency and local opportunity checks. | Profile/action log |
| Authority | Research and outreach to up to five suitable publication, directory, collaborator or mention opportunities. | Outreach log; placement is not guaranteed |
| Website care | Routine content corrections, form/link checks, backups before material changes and ordinary project uploads from complete material. | Maintenance log |
| Reporting | Plain-language completed-work report and one 30-minute review call. | Monthly review pack |

CAPACITY RULE The monthly quantities are ceilings, not a requirement to publish weak material. One excellent case study can create more value than several thin posts. Any unusually complex task is agreed before it displaces the monthly programme.

03 / SEO IN PLAIN LANGUAGE

# SEO is the work of making AMSA understandable, accessible and credible in search.

Imagine an architectural competition entry. Strong work can be overlooked if the boards are difficult to read, the project is filed in the wrong category or the key idea is missing. Search works similarly: the website needs clear content, sound technical access and signals from the wider web.

| Layer | Question it answers | Architectural analogy |
| --- | --- | --- |
| Technical SEO | Can search engines reach, read and store the pages? | Like ensuring every room is accessible, numbered and shown correctly on the plan. |
| On-page SEO | Does each page clearly explain its subject? | Like giving a project a useful title, brief, location, annotations and material description. |
| Local SEO | Can people find and verify the practice in its location? | Like a correct studio address, sign, telephone and directory entry across every public record. |
| Off-page SEO | Do relevant external sources refer to AMSA? | Like a respected publication, award body or collaborator crediting the practice and linking to the project. |
| Content | Is there enough useful evidence for a client to make a decision? | Like a portfolio that explains the thinking behind the image rather than showing an unexplained photograph. |

Google describes SEO as helping search engines understand content and helping people decide whether to visit. It also states that no one can guarantee a first-place ranking. The service therefore guarantees defined work, evidence and reporting; it does not promise a position controlled by a third party.

Google SEO Starter Guide  ·  Google guidance on hiring an SEO

04 / TECHNICAL SEO

# Technical SEO keeps the digital building open, legible and dependable.

Technical SEO is mostly invisible to a visitor, but it affects whether search engines can discover the site and whether people can use it comfortably. The monthly review identifies blockers, then the available development time is directed to the highest-value corrections.

- Crawling and indexing: check whether important pages can be discovered and stored in search engines.

- Sitemaps and robots rules: confirm the site gives sensible instructions and does not accidentally hide valuable pages.

- Status codes and broken paths: repair missing pages, broken links and inappropriate redirects.

- Canonical pages: reduce confusion when similar content is accessible through more than one URL.

- Mobile and responsive behaviour: test that layouts, navigation, galleries and forms work on common screen sizes.

- Performance: review loading, interaction and layout stability, especially for image-heavy project pages.

- Structured information: add suitable machine-readable business, organisation, article or breadcrumb information where appropriate.

- Forms and measurement: confirm enquiry paths work and important actions can be measured.

EXAMPLE A project page may look perfect on a desktop but load a 12 MB image on a phone, move while opening and have no descriptive title. Technical SEO addresses the loading and access; on-page SEO addresses the title and explanation.

Google Web Vitals  ·  Google sitemap guidance

05 / ON-PAGE, LOCAL AND OFF-PAGE SEO

# Each layer serves a different part of the client journey.

## On-page SEO: explain each project clearly

- A descriptive page title and one clear main heading.

- A concise project summary with the facts AMSA approves for publication.

- Useful subheadings: brief, context, challenge, response, materials, sustainability, team and credits.

- Image names and alternative descriptions that improve accessibility and context.

- Links to relevant services, related projects, awards and contact routes.

- A search description written for a human deciding whether the page is relevant.

## Local SEO: make the practice verifiable in Cyprus

Local work aligns AMSA's name, address, telephone, website, categories, images, services and opening information across the website and major map/business profiles. Google explains that local results mainly consider relevance, distance and prominence. Distance cannot be changed; relevance and prominence can be supported through complete information, useful pages, reviews and credible mentions.

## Off-page SEO: earn relevant references

Authority grows when credible third parties mention or cite AMSA: publishers, award bodies, universities, collaborators, suppliers, professional organisations and directories. The monthly outreach cycle prepares suitable material, contacts relevant opportunities and records the outcome. Editorial acceptance, review decisions and links remain under the publisher's control.

Google local ranking guidance  ·  Google spam policies

06 / CONTENT AND SOCIAL

# One approved project can support a month of useful communication.

AMSA supplies accurate facts, usage rights and approved images once. 404200 turns that material into formats suited to the website and selected platforms. The content remains specific to the project and avoids generic filler.

| Destination | How the source story is adapted |
| --- | --- |
| Website | A complete project story or article that becomes the source of record. |
| Instagram | A visual sequence with a concise architectural narrative and credits. |
| LinkedIn | A professional explanation of the challenge, response and relevance. |
| Facebook | A local, accessible project update linking back to the site. |
| Google Business Profile | A short practice update connected to the correct page. |
| Pinterest | Evergreen project imagery linked to the relevant portfolio page. |
| Editorial outreach | A press-ready summary, fact sheet, credits and selected images. |

## Account opening and control

- Create or claim agreed business profiles using an AMSA-owned email address where the platform permits.

- Apply the approved logo, biography, contact details, website link and consistent practice description.

- Set AMSA as the owner and 404200 as an administrator or partner, rather than making the supplier the permanent owner.

- Enable two-factor authentication and record recovery ownership with the nominated AMSA contact.

- Prepare an initial content set so a new profile does not open as an empty shell.

Google guidance on people-first content

07 / ONLINE PRESENCE MAP

# Twenty domains to assess, claim, build or approach

The aim is relevance and consistency, not mass registration. Priority profiles are created first. Architecture platforms, professional bodies and publishers are approached only when AMSA is eligible and the project is suitable. Fees, membership rules and editorial decisions are confirmed before action.

| # | Domain | Purpose | Route |
| --- | --- | --- | --- |
| 01 | Google Business Profile google.com/business | Claim and optimise the practice on Google Search and Maps. | Priority |
| 02 | Bing Places bingplaces.com | Maintain an accurate business listing for Bing and Microsoft surfaces. | Priority |
| 03 | Apple Business business.apple.com | Claim the practice on Apple Maps where the service is available. | Priority |
| 04 | LinkedIn linkedin.com | Company profile, project narratives, awards and professional updates. | Priority |
| 05 | Instagram instagram.com | Visual project storytelling, process details and studio activity. | Priority |
| 06 | Facebook facebook.com | Local discovery, news, project links and community visibility. | Priority |
| 07 | Pinterest Business business.pinterest.com | Evergreen visual discovery linked back to relevant projects. | Priority |
| 08 | YouTube youtube.com | Project films, talks, interviews and short visual explanations. | Build next |
| 09 | Vimeo vimeo.com | High-quality portfolio films and clean client-facing embeds. | Build next |
| 10 | Houzz Pro houzz.com/pro | Residential portfolio and homeowner discovery, subject to market fit. | Assess |

07 / ONLINE PRESENCE MAP CONTINUED

# Architecture, publishing and professional destinations

| # | Domain | Purpose | Route |
| --- | --- | --- | --- |
| 11 | Architizer architizer.com | Architecture-firm profile, projects and award visibility. | Build next |
| 12 | Archello archello.com | Architecture and product-community profile and project publishing. | Build next |
| 13 | ArchDaily archdaily.com/submit-a-project | Editorial project submission; acceptance is determined by the publisher. | Editorial |
| 14 | Dezeen dezeen.com/submissions | Editorial submission for suitable projects and announcements. | Editorial |
| 15 | designboom designboom.com/submissions | Editorial submission for distinctive projects and concepts. | Editorial |
| 16 | World-Architects world-architects.com | Professional architecture profile; eligibility or fees may apply. | Assess |
| 17 | Behance behance.net | Curated visual case studies for design and creative discovery. | Build next |
| 18 | Issuu issuu.com | Digital portfolios, award books, practice profiles and credentials. | Build next |
| 19 | GitHub github.com | Client-owned technical/publication archive where it adds real value. | Assess |
| 20 | ETEK etek.org.cy | Cyprus professional presence and accurate registry information where eligible. | Verify |

MONTHLY ROLLOUT Up to four profiles are created, claimed or materially completed each month until the agreed priority map is established. Ongoing activity then focuses on the channels that show clear relevance, referral traffic, engagement or publication potential.

08 / WEBSITE REBUILD

# Elementor is a visual building system inside WordPress; custom HTML and CSS complete the tailored details.

The proposed conversion keeps WordPress as the content management system and rebuilds the approved page templates with Elementor. Custom HTML and CSS are used selectively where a standard widget does not provide the required structure, responsiveness or visual precision. This is different from replacing WordPress with a fully static HTML website.

## Why the conversion matters

| Benefit | What it means for AMSA |
| --- | --- |
| Consistent templates | Project pages can follow one approved structure, so future additions feel designed rather than assembled differently each time. |
| Easier editing | Authorised users can update structured content through a visual interface while the design rules remain controlled. |
| Responsive control | Desktop, tablet and mobile layouts can be tested and adjusted deliberately. |
| Search foundations | Titles, headings, internal links, metadata, image handling, sitemaps and redirects are considered during the build rather than repaired later. |
| Maintainability | Reusable headers, footers, project templates and global styles reduce repeated manual work. |

## Why it takes time

- Inventory every public page, image, download, form, link, tracking code and important URL.

- Create reusable Elementor templates for global parts and project types.

- Rebuild the visual details and add custom HTML/CSS where necessary.

- Move approved content and optimise large images while preserving credits and quality.

- Test breakpoints, browsers, navigation, galleries, forms, accessibility and performance.

- Preserve existing URLs where practical and map permanent redirects where a URL must change.

- Run a private staging review, complete the agreed correction round, back up, launch and monitor.

PROPORTIONATE SCHEDULE For the current public-site scope, an 8-12 week staged rebuild is a realistic working range when access, content and consolidated feedback arrive on schedule. Unexpected plugins, hidden templates, new functionality or a wider redesign are assessed before they change the timeline.

Elementor and WordPress  ·  Elementor Theme Builder  ·  Google site-move guidance

09 / REBUILD DELIVERY PLAN

# The website stays live until the replacement is approved.

| Period | Focus | Included work |
| --- | --- | --- |
| Month 1 | Discover and protect | Backup, access, page/URL inventory, analytics baseline, plugin/form review, image audit, staging environment and template plan. |
| Month 2 | Build the system | Global header/footer, design tokens, project/service templates, approved content migration, responsive behaviour and initial technical SEO. |
| Month 3 | Test and release | Full staging review, consolidated correction round, forms, links, accessibility, speed, redirects, analytics, sitemap, approved launch and post-launch monitoring. |

## Boundaries that keep the work achievable

- The conversion covers the current approved public website and its repeatable page types.

- It preserves the existing visual identity; a new brand identity or unrelated redesign is a separate project.

- New portals, booking systems, ecommerce, multilingual production, complex integrations and custom applications are separate.

- One consolidated review round is included for the staged rebuild. Additional design directions are scheduled separately.

- If access, content, rights or approval is late, the affected milestone moves by the corresponding practical period.

10 / WHY SEO NEEDS SIX TO TWELVE MONTHS

# Search visibility compounds: the work can be completed quickly, while the market response develops over time.

Some changes are visible within days: a broken link can be fixed, a title can be rewritten and a profile can be completed. Solid results take longer because search engines must recrawl the site, interpret the changes, compare AMSA with other relevant results and observe a growing body of useful content and credible references.

| Period | What is happening | What AMSA can reasonably look for |
| --- | --- | --- |
| Months 1-2 | Foundation | Baseline, access, technical corrections, priority pages, profiles, first content and measurement. |
| Months 3-4 | Early evidence | More pages indexed, broader query visibility, first referral patterns and content engagement. Results may still move up and down. |
| Months 5-6 | Useful comparison | Enough completed work and data to compare themes, pages and channels more confidently. |
| Months 7-12 | Compounding | A deeper project library, stronger internal links, more external references and repeated refinement can support steadier gains. |

## Why the timing varies

- Competition: established practices and large publishers already hold years of content and links.

- Website history: existing authority, technical health and previous changes affect the starting point.

- Publishing pace: meaningful project evidence must be researched, approved and released consistently.

- Crawling and updates: search systems process pages on their own schedules and ranking systems continue to change.

- Target difficulty: a specific project/location query can move sooner than a broad, competitive phrase.

- Approvals and access: delayed facts, images or permissions reduce the volume of work search engines can evaluate.

WORKING EXPECTATION Six months is the minimum sensible period for judging a consistent programme. Twelve months gives a stronger view of seasonal behaviour, content maturity and whether visibility is translating into qualified enquiries. Neither period guarantees a ranking.

Google: effects may take days to several months  ·  Ahrefs survey: commonly 3-6 months  ·  Semrush overview: commonly 4-12 months

11 / SIX-MONTH OPERATING PLAN

# A focused sequence, with visible evidence every month

| Month | Focus | Main outputs |
| --- | --- | --- |
| 1 | Baseline and protect | Access, analytics, Search Console, crawl, content/URL inventory, account ownership, first priority correction and staging plan. |
| 2 | Publish and build | First substantial project story, social cycle, local profile work, outreach and Elementor template build. |
| 3 | Release and check | Second priority content cycle, site QA, approved launch, redirect/index monitoring and first quarterly review. |
| 4 | Expand what works | Improve pages gaining impressions, build the next project story, complete priority profiles and continue relevant outreach. |
| 5 | Strengthen authority | Deeper internal linking, awards/publication evidence, collaboration credits and focused editorial submissions. |
| 6 | Evaluate and choose | Six-month evidence review: visibility, qualified visits, enquiries, completed work, lessons and the next six-month recommendation. |

## What the monthly report will show

- Work completed and live URLs, so AMSA can see the output rather than only a score.

- Search impressions, clicks, relevant queries and priority pages from Search Console.

- Website engagement and agreed key events such as contact clicks, form submissions or project-depth visits.

- Local-profile actions and completeness, where platform data is available.

- Social publications, meaningful engagement and traffic back to the website.

- Outreach sent, replies, placements and next opportunities.

- Risks, dependencies and the next priority in plain language.

Google Search Console performance reporting

12 / WORKING RELATIONSHIP

# Clear inputs keep the programme moving.

| Area | Practical arrangement |
| --- | --- |
| AMSA provides | Accurate project facts; approved images and credits; publication rights; access; one nominated approver; notice of private addresses, embargoes and confidential material. |
| 404200 provides | Research, writing, design adaptation, technical implementation, publishing, outreach, quality checks, completed-work reporting and the next priority. |
| Approval method | One consolidated round of feedback. Nothing is published without written approval. Silence is not approval. |
| Account ownership | AMSA remains owner of the domain, website, analytics, business profiles and social accounts. 404200 receives the minimum administration access needed. |
| External costs | Hosting, domains, paid media, premium licences, photography, translation, paid placement and membership fees require separate written approval. |

## Investment

| Option | Amount |
| --- | --- |
| Monthly service value | EUR 350 per month |
| Quarterly billing | EUR 1,050 paid every three months in advance |
| Semi-annual billing | EUR 2,100 paid every six months in advance |
| VAT | Added only if legally chargeable |

CLIENT CHOICE The service is designed as a six-month SEO programme. The Client may end the agreement at any time under the attached agreement; unused complete prepaid months are refunded after completed work and approved third-party costs are reconciled.

13 / DECISION

# Recommended decision for the meeting

- Confirm the priority project type, client audience and geographic market.

- Select the first three projects AMSA may explain and promote.

- Name one person who can approve facts, images, credits and publication.

- Choose quarterly or semi-annual payment.

- Approve the six-month working plan and schedule the access/kickoff session.

PROPOSED START On signature, cleared payment and sufficient access, 404200 begins the baseline and first priority queue. The current website remains live while the Elementor rebuild is prepared privately.

# Sources and further reading

01  AMSA homepage

02  AMSA About page

03  AMSA Competitions & Awards

04  Google SEO Starter Guide

05  Google: helpful, reliable, people-first content

06  Google: deciding whether you need an SEO

07  Google Business Profile: local ranking

08  Google Search Central: site moves and migrations

09  Google Search Central: core updates and timing

10  Google Search Console performance report

11  Google Web Vitals

12  Elementor: WordPress and Elementor

13  Elementor Theme Builder

14  Ahrefs: how long SEO takes

15  Semrush: how long SEO takes

## Platform links for the 20-domain map

01  Google Business Profile — google.com/business

02  Bing Places — bingplaces.com

03  Apple Business — business.apple.com

04  LinkedIn — linkedin.com

05  Instagram — instagram.com

06  Facebook — facebook.com

07  Pinterest Business — business.pinterest.com

08  YouTube — youtube.com

09  Vimeo — vimeo.com

10  Houzz Pro — houzz.com/pro

11  Architizer — architizer.com

12  Archello — archello.com

13  ArchDaily — archdaily.com/submit-a-project

14  Dezeen — dezeen.com/submissions

15  designboom — designboom.com/submissions

16  World-Architects — world-architects.com

17  Behance — behance.net

18  Issuu — issuu.com

19  GitHub — github.com

20  ETEK — etek.org.cy